## Training Agenda
Session ID | Title | Type | Duration (hours) | Audience | Participants target | Lead | Deliverables | Acceptance Criteria | Scheduled (relative) | Estimated Effort (hours)
S1 | Leadership Workshop (In-person) | Presential | 6 | Leadership | 12-15 | Líder de Formação | workshop_materials.zip;attendance_list.csv | Workshop delivered; post-survey avg >=4/5 | Month 3 Week 1 | 24
S2 | Webinar: Sensitization (synchronous) | Webinar | 2 | Managers & HR | ~50 | Líder de Formação | webinar_recording.mp4;slides.pdf | Recording + participant list; post-webinar survey | Month 3 Week 2 | 12
S3 | Webinar: Practical Accommodations | Webinar | 2 | HR & Operations | ~50 | Líder de Formação | webinar_recording.mp4;checklist.pdf | Recording + action checklist; participant list | Month 4 Week 1 | 12
S4 | E-learning Module 1: Accessibility Basics | E-learning | 2 | All employees | Self-paced | Equipe de Pesquisa / Líder de Formação | module1_content.zip;quiz.csv | Module published + quiz operational; completion metrics available | Month 3-5 | 40
S5 | E-learning Module 2: Inclusive Communication | E-learning | 2 | All employees | Self-paced | Líder de Formação | module2_content.zip;quiz.csv | Module published + quiz operational; completion metrics available | Month 3-5 | 40
S6 | Multipliers Kit & Microtraining | Microtraining | 1 | Multiplicadores | ~20 | Coordenador de Comunidade | multipliers_kit.zip;microtraining_guide.pdf | Kit delivered; 1 micro-session delivered; adoption plan | Month 4 Week 2 | 16
S7 | Post-training assessment & report | Assessment | 8 | Project Team | — | Analista de Dados | post_training_report.pdf;dashboard | Assessment completed; dashboard with KPIs delivered | Month 6-7 | 20