## Timeline
Milestone | Start (relative) | End (relative) | Owner | Acceptance criteria | Estimated Hours
Kickoff & Alinhamento | Week 0 | Week 0 | PM (DiverCidade) | Governance document and approved project plan | 8
Diagnóstico (coleta) | Month 1 | Month 2 | Equipe de Pesquisa | Survey + 4 focus groups + barriers map | 120
Análise & Priorização | End Month 2 | End Month 2 | PM / Analista | Barriers report and prioritized roadmap | 40
Capacitação | Month 3 | Month 5 | Líder de Formação | Workshops delivered and post-training survey | 120
Implementação estrutural | Month 4 | Month 7 | PM / Área Responsável | Implementation of agreed accommodations/policies | 160
Consolidação & relatório final | Month 8 | Month 8 | PM / Analista de Dados | Final report and dashboard delivered | 60